## Sheet1
Area Path | Assigned To | Iteration Path | Work Item Id | Title | State | Work Item Type | Created Date | Closed Date | Resolved Date
GMB Project by MERP\Team GMB | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 2213 | Test case 1262 (MERP) 1978 (GMB)Submissions: New/Upgrade Software and Equipment Submissions Non-TLS - Blocked by pop up error message | New | Bug | 5/31/2025 9:32:54 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2205 | Polaris: Non-TLS Submission: AD Review - Approval Letter sections should be blank | Closed | Bug | 5/30/2025 10:00:35 AM -07:00 | 6/2/2025 8:51:29 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2150 | Polaris: Submissions Status - Change "Pending Payment" and "Processing Refund" into two separate statuses. | Closed | Bug | 5/22/2025 10:43:03 AM -07:00 | 5/23/2025 9:00:20 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2502 | 1219 | Correct text from "Submission_Name" to "Submission Name" | Closed | Bug | 3/2/2025 2:27:27 PM -08:00 | 3/3/2025 10:27:51 AM -08:00 | 3/3/2025 10:24:05 AM -08:00
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2502 | 1220 | Correct text from "Component_Name" to "Component Name" | Closed | Bug | 3/2/2025 2:43:11 PM -08:00 | 3/3/2025 10:28:16 AM -08:00 | 3/3/2025 10:25:36 AM -08:00
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2502 | 1221 | Correct Text from "Issue_No" to "Issue No." | Closed | Bug | 3/2/2025 2:46:24 PM -08:00 | 3/3/2025 10:28:59 AM -08:00 | 3/3/2025 10:25:32 AM -08:00
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2153 | My Account: When creating a Non-TLS Submission the page opens to Documents tab | Closed | Bug | 5/22/2025 12:03:14 PM -07:00 | 5/23/2025 8:55:09 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2154 | My Account: Non-TLS Submission - Add "Non-TLS Submission Documents" as an upload category | Closed | Bug | 5/22/2025 12:18:38 PM -07:00 | 5/27/2025 5:55:49 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2162 | Polaris: non-TLS Submission -- Once unassigned submission is assigned it should not appear in the "non-TLS unassigned" queue | Closed | Bug | 5/23/2025 11:38:19 AM -07:00 | 5/27/2025 9:54:42 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2161 | Polaris: Non-TLS Submission - PDF button is not populating | Closed | Bug | 5/23/2025 10:25:44 AM -07:00 | 5/27/2025 9:57:24 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1688 | My Account: TLS Equipment/Software Submission - Previous Submission field does not look up Previous Submissions | Non Issue | Bug | 5/1/2025 1:48:55 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1689 | My Account: Non-TLS Equipment/Software Submission - Add Existing Software Submission lookup is blank | Closed | Bug | 5/1/2025 1:54:23 PM -07:00 | 5/15/2025 5:33:12 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1867 | My Account: Non-TLS Equipment/Software Submission - Missing Instructions Tab | Closed | Bug | 5/7/2025 8:37:22 AM -07:00 | 5/15/2025 5:35:28 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1869 | Polaris & MyAccount: Non-TLS Equipment or Software - Missing Submission Checklist in non-TLS Summary tab | Closed | Bug | 5/7/2025 8:53:35 AM -07:00 | 5/20/2025 11:21:27 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1871 | MyAccount: Submissions Dashboard - Type of Submissions column should display the type of form selected. | Closed | Bug | 5/7/2025 9:17:06 AM -07:00 | 5/15/2025 5:41:16 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1894 | My Account & Polaris: Add Version Number field in Summary tab of TLS Submission | Closed | Bug | 5/8/2025 10:15:30 AM -07:00 | 5/15/2025 5:46:13 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1895 | My Account: TLS Submission - If the Game is a Software add "Under $5 min bet?" and "$30 max bet?" fields in Summary tab. | Closed | Bug | 5/8/2025 10:27:24 AM -07:00 | 5/20/2025 11:23:45 AM -07:00 | null
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2054 | Test case 1265 (MERP) 1757 (GMB) My Account: Submissions Page Design - Submission withdraw pop up menu cancel does not work | Resolved | Bug | 5/14/2025 4:49:09 PM -07:00 | null | 5/30/2025 7:30:32 AM -07:00
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2055 | Test Case 1265 (MERP) 1757 (GMB) My Account: Submissions Page Design - Submission view details pop up summary "close" button does not work | Resolved | Bug | 5/14/2025 4:58:52 PM -07:00 | null | 5/30/2025 7:31:13 AM -07:00
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2070 | Test case 1262 (MERP) 1978 (GMB) Submissions: New/Upgrade Software and Equipment Submissions Non-TLS - Incorrect Data Formatting | Resolved | Bug | 5/15/2025 10:12:13 AM -07:00 | null | 6/2/2025 8:47:52 AM -07:00
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2360 | Unable to Select or Enter a license number for Non-TLS submission | Non Issue | Bug | 6/7/2025 8:10:29 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2357 | TLS Submission - Unable to move past draft status in Polaris when entering in a TLS submission manually. | Non Issue | Bug | 6/7/2025 7:18:15 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2319 | June GMB UAT - Out of State Non-TLS Submission: Not accepting Location Name or Mailing Address | Duplicate | Bug | 6/5/2025 4:34:02 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2318 | June GMB UAT - Polaris Submissions: Assigned To Column is blank | Non Issue | Bug | 6/5/2025 4:23:25 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2331 | June GMB UAT - MyAccount: User unable to delete uploaded documents in draft status for non-TLS submission | Closed | Bug | 6/6/2025 8:17:17 AM -07:00 | 6/19/2025 6:33:31 AM -07:00 | null
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2358 | Home Run Error Type in Polaris for TLS Submissions is incorrect language | Closed | Bug | 6/7/2025 7:33:57 PM -07:00 | 6/19/2025 6:34:31 AM -07:00 | null
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP | 2058 | Test Case 1265 (MERP) 1757 (GMB) My Account: Submissions Page Design - Secific test data needs to be created to complete test | Duplicate | Bug | 5/14/2025 6:08:46 PM -07:00 | null | null
GMB Project by MERP\Team Ace of Spades | Dash, Ankita (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1556 | Clicking on Customer Payment Journal under Payments saying Alert "Required batch not running" | Non Issue | Bug | 4/11/2025 3:42:16 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1254 | MyAccount: United States Military Service Tab-End of Service date accepts the date earlier than the Start date and Start of Service Date allows Future Dates for Military Service. | Closed | Bug | 3/5/2025 11:18:37 AM -08:00 | 4/21/2025 7:59:36 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2320 | Polaris Renewal: New Application Questions Displaying on Renewal Application – Application Summary Tab | Testing - QA | Bug | 6/5/2025 8:09:00 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1632 | MyAccount: United States Military Service tab: "Type of Discharge" field shows no options | Closed | Bug | 4/23/2025 5:13:09 AM -07:00 | 4/30/2025 7:13:28 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1597 | MyAccount: Documents Page: Document category options are not available for selection. | Closed | Bug | 4/14/2025 11:28:10 AM -07:00 | 5/1/2025 10:51:41 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1668 | My Account - new application initiated by the employer should not include the 'Tribal Employer Authorization' title under the 'Application Oath' tab for a non-tribal organization/employer | Closed | Bug | 4/29/2025 2:17:21 PM -07:00 | 5/2/2025 5:32:20 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1248 | Missing Individual License Types (Commercial Gambling Manager and Enhanced Raffle Call center Representative ) in Look up | Closed | Bug | 3/4/2025 3:19:30 PM -08:00 | 4/8/2025 1:28:24 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1474 | MyAccount: Contact Information Tab: "Cancel" button and Close Icon (X) not functioning on "Add Alternate Name" Pop-up. | Closed | Bug | 4/8/2025 10:26:32 AM -07:00 | 4/14/2025 7:55:59 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1279 | Individual Applications- Missing "Save", "Save and Exit" buttons on pages. | Closed | Bug | 3/7/2025 11:38:13 AM -08:00 | 4/21/2025 12:27:34 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1257 | Documentation tab- State ID Identification card Should be "state identification card" | Closed | Bug | 3/5/2025 2:25:33 PM -08:00 | 4/30/2025 7:00:12 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1256 | Criminal History Tab-Missing Some Information and No option to remove the added Criminal History record. | Closed | Bug | 3/5/2025 1:04:44 PM -08:00 | 4/30/2025 7:03:22 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1249 | Missing Headers for Information in Application Oath Page. | Closed | Bug | 3/5/2025 8:00:06 AM -08:00 | 4/30/2025 12:08:28 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1473 | MyAccount: Redirected to Application License Type Tab After Saving Alternate Name from Pop-Up on Contact Information Page. | Closed | Bug | 4/8/2025 10:08:31 AM -07:00 | 4/30/2025 7:02:20 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1480 | MyAccount: Criminal History Tab: Error on Saving the Criminal History Charge Information | Closed | Bug | 4/8/2025 2:09:25 PM -07:00 | 5/1/2025 4:36:53 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1484 | MyAccount: Application License Type: Incorrect Display of License Type Names. | Closed | Bug | 4/8/2025 7:49:07 PM -07:00 | 4/30/2025 7:04:49 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1620 | MyAccount: Incorrect tab name displaying as " Default Text // In case none of the conditions are met" Instead of "Application License Type" | Closed | Bug | 4/21/2025 12:53:38 PM -07:00 | 4/30/2025 7:11:46 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1621 | MyAccount: "Apply for a New License" button displays "Application form not available" instead of opening Individual Applications. | Closed | Bug | 4/21/2025 7:53:50 PM -07:00 | 4/30/2025 7:12:06 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1630 | My Account: "Save and Next" button in Contact Information tab does not validate required fields | Closed | Bug | 4/22/2025 9:24:53 PM -07:00 | 4/30/2025 7:12:28 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1498 | MyAccount: Contact Information Tab: DOB field allowing the date which is lesser than 18 years old. | Closed | Bug | 4/9/2025 2:33:32 PM -07:00 | 5/1/2025 3:41:45 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1631 | MyAccount: "Submit" Button not working on the Application Oath tab. | Closed | Bug | 4/23/2025 4:57:41 AM -07:00 | 4/30/2025 7:12:47 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2326 | Polaris Renewal: Task Not Created for LS when Alert is present for an Individual | Testing - QA | Bug | 6/6/2025 5:51:32 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2321 | Polaris Renewal: Checklist Document Missing for Renewal Application in CRM (Checklist Tab) | Testing - QA | Bug | 6/5/2025 8:21:02 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2325 | Polaris Renewal: Task Not Created for Licensing Specialist (LS) When Case Exists | Testing - QA | Bug | 6/6/2025 5:24:35 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1691 | MyAccount: Contact Information - Incorrect Title for Alternate Names field | Closed | Bug | 5/1/2025 3:23:06 PM -07:00 | 5/2/2025 4:51:10 AM -07:00 | 5/2/2025 4:51:10 AM -07:00
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1701 | MyAccount: Employer/Certification- Incorrect Field Label Displayed for Date of Birth (DOB) Field | Closed | Bug | 5/1/2025 10:14:26 PM -07:00 | 5/2/2025 5:20:21 AM -07:00 | 5/2/2025 5:20:21 AM -07:00
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1702 | MyAccount: Employee/Employer/Certification- "Liquid error: Value cannot be null. Parameter name: key" Displayed on Application | Closed | Bug | 5/1/2025 10:26:42 PM -07:00 | 5/2/2025 5:22:02 AM -07:00 | 5/2/2025 5:22:02 AM -07:00
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1275 | Card Room Employee Questions Tab- Class Name Display in Dropdown should be 'Class A' and 'Class B' instead of A and B | Closed | Bug | 3/7/2025 8:58:02 AM -08:00 | 5/1/2025 5:02:56 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1676 | My Account: Employee-License questions: Explanation Field Incorrectly Set as Required When License Denial Question Is Answered 'Yes' | Closed | Bug | 4/30/2025 9:45:43 PM -07:00 | 5/5/2025 7:31:17 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1690 | MyAccount: Pending Class III Applications are incorrectly appearing under the "Employee Individual - My Pending Applications" section | Closed | Bug | 5/1/2025 3:05:06 PM -07:00 | 5/5/2025 8:03:20 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1259 | Licensee Questions: Missing License Question on Application for Service Supplier Representative License type | Closed | Bug | 3/5/2025 4:09:02 PM -08:00 | 5/5/2025 5:08:55 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1260 | Licensee Questions Page- Missing License question on application for Sports wagering License types (Major, Mid-Level, Ancillary sports wagering representative ) | Closed | Bug | 3/5/2025 4:21:52 PM -08:00 | 5/5/2025 5:08:43 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1487 | MyAccount: License Questions-Specific fields related to Cardroom employee | Closed | Bug | 4/9/2025 7:32:00 AM -07:00 | 5/5/2025 5:09:23 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1652 | MyAccount - Employee submitting new application - Oath tab has incorrect links and verbiage | Closed | Bug | 4/29/2025 7:50:16 AM -07:00 | 5/2/2025 2:24:39 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1669 | My Account - Employer initiated individual application should have the 'Oath' verbiage matching with the field listing | Closed | Bug | 4/29/2025 2:24:53 PM -07:00 | 5/6/2025 6:45:30 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1666 | MyAccount: Employer initiated application for Sales Representative required question | Closed | Bug | 4/29/2025 1:55:36 PM -07:00 | 5/6/2025 6:38:15 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2502 | 1662 | MyAccount - Application submitted by the employee stays in 'Draft' status | Closed | Bug | 4/29/2025 11:23:10 AM -07:00 | 5/1/2025 4:55:40 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1483 | MyAccount: Criminal History Tab: "Cancel" button and Close Icon (X) not functioning on "Add criminal History Record" Pop-up. | Closed | Bug | 4/8/2025 7:18:33 PM -07:00 | 4/14/2025 7:53:20 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1485 | MyAccount: Missing Content in Application Oath and Documentation Tabs | Closed | Bug | 4/9/2025 6:28:44 AM -07:00 | 4/14/2025 7:54:11 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1488 | MyAccount: Missing "Please enter previous used names" instructional text after select Yes to "Have you ever used a different name?" | Closed | Bug | 4/9/2025 10:34:49 AM -07:00 | 4/14/2025 7:56:52 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1530 | MyAccount: Contact Information Page: Mailing address fields are not displayed when "Same as home address?" checkbox is selected. | Closed | Bug | 4/10/2025 7:53:15 PM -07:00 | 4/14/2025 8:20:45 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1280 | Application Oath Page: Missing UI message after submits the application | Closed | Bug | 3/7/2025 12:01:59 PM -08:00 | 4/14/2025 10:58:18 AM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1252 | Licensee Questions Tab- All Questions displayed Instead of conditional display based on "Yes" Selection. | Closed | Bug | 3/5/2025 10:08:24 AM -08:00 | 4/8/2025 1:29:25 PM -07:00 | null
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1251 | MyAccount: Contact Information Tab: Missing Required Fields and Incorrect Field Labels in Contact Information Tab | Closed | Bug | 3/5/2025 9:04:59 AM -08:00 | 4/18/2025 1:37:16 PM -07:00 | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2027 | Test Case 1272 (MERP) 1747 (GMB) MyAccount/Application/Cardroom employee default should be blank | Duplicate | Bug | 5/14/2025 11:24:54 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2030 | Test Case 1272 (MERP) 1747 (GMB) MyAccount/Application/Cardroom employee Exit button not working | Duplicate | Bug | 5/14/2025 11:34:07 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2062 | Test Case 1425 (MERP) 1772 (GMB) MyAccount: System allows for future dated Military Service dates for class III application | Deferred | Bug | 5/15/2025 7:59:10 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2023 | Test Case 1203 (MERP) MyAccount Employee Individual Application - Alternate name does not display when saved | Duplicate | Bug | 5/14/2025 10:59:56 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2029 | Test case 1324 (MERP) 1763 (GMB) MyAccount: Contact Information for New Application Request Initiated by the Employer/Certification - Liquid Error | Cannot Recreate | Bug | 5/14/2025 11:34:00 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2037 | Test Case 1270 (MERP) 1746 (GMB) MyAccount Documentation Tab - clickable link not working | Resolved | Bug | 5/14/2025 1:09:55 PM -07:00 | null | 5/27/2025 8:23:59 AM -07:00
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2072 | Test case 1318 (MERP) 1974 (GMB) Test Case: My Account & Polaris - Organization License Templates - Organization, Premise and Limited Time Duration Permit - License Does Not Generate | Resolved | Bug | 5/15/2025 10:15:50 AM -07:00 | null | 5/16/2025 6:19:44 AM -07:00
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2017 | Test case 1560 (MERP) 1774 (GMB) MyAccount: USPS Address Validation for Organization and Individual - USPS Validation not working in Polaris | Duplicate | Bug | 5/14/2025 10:05:05 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2063 | Test Case 1425 (MERP) 1772 (MERP) MyAccount: US Military Service and Criminal History Information for Class III Certification Request Initiated by the TGA - Unable to save Contact Information | Closed | Bug | 5/15/2025 8:21:14 AM -07:00 | 6/1/2025 8:37:27 PM -07:00 | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2160 | Test Case 1324 (MERP) 1763 (GMB) MyAccount: Contact Information for New Application Request Initiated by the Employer/Certification - Save & Next does not advance user | Resolved | Bug | 5/23/2025 4:20:39 AM -07:00 | null | 6/2/2025 7:23:54 AM -07:00
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2202 | Renewal: UAT-Employer/ Employee- Error When Removing Criminal History Record Using "Remove" Button | Closed | Bug | 5/29/2025 5:00:48 PM -07:00 | 5/30/2025 6:21:42 AM -07:00 | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2366 | US 984 - My Account: License Applications available to Individuals, Tribes, Corporations (FP and NFP) in My Account - name change/add employer not available for employer login | Non Issue | Bug | 6/8/2025 1:17:27 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2430 | June GMB UAT - My Account Application: building an individual app (for address verification) | Duplicate | Bug | 6/11/2025 3:00:00 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2035 | Test case 1270 (MERP) 1746 (GMB) My Account: New Individual application submission by Employee - Future military start date allowed | Dev Complete | Bug | 5/14/2025 12:59:09 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2025 | Test Case 1593 (MERP) 1745 (GMB) MyAccount/Application/Tribal Class III, system pulling DOB | Dev Complete | Bug | 5/14/2025 11:10:58 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2026 | Test Case 1593 (MERP) 1745 (GMB) MyAccount/Application/Class III app/Contact information tab, deletion of saved data | Deferred | Bug | 5/14/2025 11:12:31 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1667 | TGA MyAccount: Credential Tab Missing When Initiating Class III Eligibility and Registration from Licensing Page | Closed | Bug | 4/29/2025 2:10:29 PM -07:00 | 5/5/2025 8:11:38 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1677 | MyAccount: Certification/Employer/Employee: United States Military Tab: The Military fields are Incorrectly marked as required | Closed | Bug | 4/30/2025 10:09:40 PM -07:00 | 5/5/2025 7:55:26 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2142 | Renewal: Employer -'Mid-Level Sports Wagering Vendor Representative' License Application Opens When User Attempts to Renew 'Ancillary Sports Wagering Representative' License | Closed | Bug | 5/21/2025 6:38:28 PM -07:00 | 5/22/2025 6:26:58 AM -07:00 | 5/22/2025 6:26:58 AM -07:00
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2135 | Renewal: Employer-Some user-indicated fields are not reflected correctly or are missing when the submitted application is viewed. | Closed | Bug | 5/21/2025 9:47:10 AM -07:00 | 5/27/2025 12:33:29 PM -07:00 | 5/27/2025 5:51:21 AM -07:00
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2133 | Renewal: Employer--Incorrect application opens when employer initiates renewal for Employee Type Application from Super User Dashboard | Closed | Bug | 5/21/2025 8:34:02 AM -07:00 | 5/29/2025 5:48:32 PM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2130 | Renewal: Employer-Contact Information of Employee Not Auto-Filled on Contact Information Tab. | Closed | Bug | 5/21/2025 7:45:35 AM -07:00 | 5/29/2025 5:54:09 PM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2143 | Renewal – Employee/Employer: Sports Wagering Question Defaults to 'No' Instead of 'Blank' in Major/Mid-Level/Ancillary Renewal Applications | Closed | Bug | 5/21/2025 6:49:38 PM -07:00 | 5/30/2025 4:47:54 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1670 | TGA MyAccount: Certification-Document Upload: After uploading the documents, User is redirected to Contact Information Tab. | Closed | Bug | 4/29/2025 2:42:34 PM -07:00 | 5/5/2025 6:09:18 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1700 | Documents tab: Employee/Employer Uploading Documents Redirects User to Contact Information Tab | Closed | Bug | 5/1/2025 10:00:41 PM -07:00 | 5/5/2025 8:25:26 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1665 | TGA MyAccount: Incorrect Status and Missing Applicant Name in "My Pending Applications" for Class III Certification | Closed | Bug | 4/29/2025 1:34:39 PM -07:00 | 5/5/2025 10:58:21 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1693 | Criminal History: Employee/ Employer/Certification: Criminal History Date Field Accepts Manually Entered Future Dates | Closed | Bug | 5/1/2025 5:05:37 PM -07:00 | 5/6/2025 8:41:23 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1695 | Alternate Names: Employer/Certification: Geeting an error while adding the Alternate names | Closed | Bug | 5/1/2025 7:28:12 PM -07:00 | 5/6/2025 8:44:05 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1698 | My Account: Employee/Employer/Certification- Submitted Application Remains Editable – Should Be Read-Only | Closed | Bug | 5/1/2025 9:24:44 PM -07:00 | 5/6/2025 8:22:41 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1708 | MyAccount: Employer-Unable to Enter Primary Email Address in Contact Information Tab | Closed | Bug | 5/2/2025 12:01:45 PM -07:00 | 5/6/2025 8:09:07 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1622 | Polaris: USPS Validation does not handle missing or incorrect Apartment/Suite numbers | Closed | Bug | 4/21/2025 9:10:06 PM -07:00 | 5/6/2025 8:53:54 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2128 | "Renewal: Employer-Missing Employer Information Message for 'Linked Bingo Prize Provider Representative' License Type | Closed | Bug | 5/21/2025 7:34:55 AM -07:00 | 5/21/2025 7:28:33 PM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2129 | Renewal: Employer- Missing Employer Information Message for 'Enhanced Raffle Call Center Representative' License Type | Closed | Bug | 5/21/2025 7:38:53 AM -07:00 | 5/21/2025 7:38:00 PM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2134 | Renewal: Employer -Incorrect License Type Populating During Employer Renewal for 'Mid-level Sports Wagering Vendor Representative' License | Closed | Bug | 5/21/2025 9:06:45 AM -07:00 | 5/22/2025 6:28:56 AM -07:00 | 5/22/2025 6:28:56 AM -07:00
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1500 | MyAccount: Field validations on Contact Information page in New/Renewal Individual applications | Closed | Bug | 4/9/2025 3:16:54 PM -07:00 | 6/2/2025 9:33:49 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1696 | My Account: Employee/Employer/Certification: Yes/No Option questions defaulted to 'NO' Instead of 'Blank' | Closed | Bug | 5/1/2025 8:57:50 PM -07:00 | 5/30/2025 7:09:02 AM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1725 | My Account: Employee/Employer/Certification: Exit Button Navigation Issues in License Questions/Certification Questions, and US Military Service Tabs | Closed | Bug | 5/5/2025 2:52:16 PM -07:00 | 5/30/2025 12:53:43 PM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2167 | Related Cases: Individual- Linked Case Still Visible in Related Cases Section After Confirmation | Closed | Bug | 5/26/2025 8:21:57 PM -07:00 | 6/2/2025 1:23:01 PM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2168 | Related Cases: Individual- Linked case incorrectly appears under Related Cases tab for the same individual | Closed | Bug | 5/26/2025 8:27:31 PM -07:00 | 6/2/2025 1:28:01 PM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2208 | Test Case 1560 (MERP) 1774 (GMB) MyAccount: USPS Address Validation for Organization and Individual - | Cannot Recreate | Bug | 5/30/2025 12:25:24 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 1705 | MyAccount: Eligibility- Alternate names: Removed Alternate Names Reappear After Adding a couple of New Ones | Closed | Bug | 5/2/2025 6:17:26 AM -07:00 | 6/9/2025 7:24:06 PM -07:00 | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2507 | 1719 | My Account: Certification: Pre-Certification and Conditional Certification Specific Document Fields Incorrectly Set as Optional | Deferred | Bug | 5/5/2025 7:04:41 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 1721 | My Account: Non-Tribal And Tribal Applications: Document link in Uploaded Documents Section redirects to Error Page | Dev Ready | Bug | 5/5/2025 1:23:07 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2507 | 1697 | Document Category Options: Employee/Employer- The Tribal Document Category options displayed under Non-Tribal Individual Application Document category dropdown. | Deferred | Bug | 5/1/2025 9:02:30 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2268 | Renew button is enabled one day before the start of the active renewal period | Dev Complete | Bug | 6/4/2025 1:21:13 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 1699 | My Account-Criminal History: Employee/Employer/Certification: Missing Prefix Text in Questions: "Have You Ever / Has Your Employee" | Testing - QA | Bug | 5/1/2025 9:29:42 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 1703 | MyAccount: Employee/ Employer/Certification- End of Service Date Field Does Not Accept Manual Entry | Testing - QA | Bug | 5/1/2025 10:44:26 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 1722 | Tribal Class III Eligibility & Registration new application employee search option is not working | Development | Bug | 5/5/2025 2:24:10 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Koppuravuri, Sai (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1255 | My Account Licensing dashboard should not display the time stamp for the effective and expiration date | Closed | Bug | 3/5/2025 11:50:45 AM -08:00 | 3/6/2025 6:45:23 AM -08:00 | 3/5/2025 1:26:12 PM -08:00
GMB Project by MERP\Team Black Jack | Lin, Yaoshi (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2317 | June GMB UAT - EGL Role Based Access: Edit Submissions Read Only | Development | Bug | 6/5/2025 4:19:53 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Lin, Yaoshi (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2233 | June GMB UAT - MyAccount Duplicate Secondary User - QLR Filer profile allowed | Testing - QA | Bug | 6/3/2025 8:31:19 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Lin, Yaoshi (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1512 | Premise Address Sub Grid not displaying new entries | Closed | Bug | 4/10/2025 8:17:30 AM -07:00 | 5/22/2025 11:38:53 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Lin, Yaoshi (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1513 | Social Security # allows less than 9 digits | Closed | Bug | 4/10/2025 8:28:43 AM -07:00 | 5/22/2025 11:39:01 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Lin, Yaoshi (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1684 | Secondary User: Payment Submitter: Non-Tribal Account Dashboard and Menu | Closed | Bug | 5/1/2025 10:17:08 AM -07:00 | 5/28/2025 9:47:29 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Lin, Yaoshi (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1650 | Tribal Super User Dashboard | Non Issue | Bug | 4/29/2025 1:23:23 AM -07:00 | null | null
GMB Project by MERP\Team GMB | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2459 | GMB 2295 (Copy of MERP 2105) My Account: Non-Tribal Account: Individual Profile Page - Not able to verify Personal Information with any user id | Duplicate | Bug | 6/12/2025 11:56:53 AM -07:00 | null | null
GMB Project by MERP\Team GMB | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2452 | Test case 2300 (GMB) 2210 (MERP) Canned Notification sent to Personal Email Address - attachment does not open in MyAccount | Non Issue | Bug | 6/12/2025 10:21:52 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2410 | June GMB UAT - My Account US 1863 Secure Message Center: Enquiry Routing Based on Selected Subject | Non Issue | Bug | 6/10/2025 7:00:26 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2487 | Test case 2300 (GMB) 2210 (MERP) Canned Notification sent to Personal Email Address - Attachment does not open, new browser opens instead | New | Bug | 6/17/2025 9:18:05 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP | 2061 | Test case 1601 (MERP) 1759 (GMB) My Account: Super User: Manage Requests - User Request grid not present/ Not clickable from dashboard | Non Issue | Bug | 5/15/2025 7:55:14 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP | 2097 | Test Case 1577 (MERP) 1724 (GMB)Create Account Alerts- unable to open Notes and Alerts due to permissions | Duplicate | Bug | 5/15/2025 4:06:06 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP | 2065 | Test Case 1203 (MERP) 1742 (GMB) My Account: Contact Information on New Individual Application by Employee - My account allows users to access previous users work | Duplicate | Bug | 5/15/2025 9:10:33 AM -07:00 | null | null
GMB Project by MERP\Team GMB | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2448 | Incorrect Address Validation - USPS | Non Issue | Bug | 6/12/2025 9:20:01 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2074 | Test case 1210 (MERP) 1959 (GMB) Test Case: New/Edit Individual Info - Field Validation | Resolved | Bug | 5/15/2025 10:17:22 AM -07:00 | null | 5/28/2025 11:35:58 AM -07:00
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2075 | Test case 1210 (MERP) 1959 (GMB) Test Case: New/Edit Individual Info - Incorrectly Required Fields | Resolved | Bug | 5/15/2025 10:18:00 AM -07:00 | null | 5/28/2025 11:35:58 AM -07:00
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2076 | Test case 1210 (MERP) 1959 (GMB) Test Case: New/Edit Individual Info - Incorrect Field Data Values | Resolved | Bug | 5/15/2025 10:18:34 AM -07:00 | null | 5/28/2025 11:35:58 AM -07:00
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP | 2048 | Test Case 1463 (MERP) 1753 (GMB) My Account: Non-Tribal: Super User Dashboard and Menu options - Grid names do not match | Resolved | Bug | 5/14/2025 2:58:50 PM -07:00 | null | 5/27/2025 11:58:12 AM -07:00
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2351 | June GMB UAT - Polaris: Administrative Assistant Role Access - Org Notes | Non Issue | Bug | 6/6/2025 4:21:27 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2352 | June GMB UAT - Polaris: Administrative Assistant Role Access - Create Individual | Non Issue | Bug | 6/6/2025 4:23:16 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2354 | June GMB UAT - Polaris: Administrative Assistant Role Access - Individuals Notes | Non Issue | Bug | 6/6/2025 4:26:03 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2363 | ITD QA - MyAccount - No Prompt for QLT # | Non Issue | Bug | 6/8/2025 12:01:22 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2085 | Test Case 1441 (MERP) 1949 (GMB) My Account: Switch Profiles - Incorrect Option Available | Testing - QA | Bug | 5/15/2025 2:11:17 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2365 | Unable to Add Super User | Testing - QA | Bug | 6/8/2025 12:36:15 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2313 | June GMB UAT - My Account: Invalid Account Access on Switch Profile | Testing - QA | Bug | 6/5/2025 3:49:12 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2221 | Case Management: Case Report: Person mailing address is copied from Location of Address field. | Closed | Bug | 6/2/2025 8:24:53 AM -07:00 | 6/12/2025 7:16:17 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2223 | Case Management: The case report times are in UTC. Please update them to match system date times. | Closed | Bug | 6/2/2025 8:55:28 AM -07:00 | 6/12/2025 7:45:40 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2011 | Case Management: Model field missing in Vehicle details page. | Closed | Bug | 5/13/2025 11:04:01 AM -07:00 | 5/22/2025 8:09:43 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1247 | Audit History not capturing the changes | Closed | Bug | 3/4/2025 2:42:46 PM -08:00 | 3/5/2025 8:29:38 AM -08:00 | 3/4/2025 3:00:19 PM -08:00
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1507 | Violation Grid updates | Closed | Bug | 4/10/2025 7:35:31 AM -07:00 | 4/29/2025 5:40:24 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1508 | Two Violation Tabs | Closed | Bug | 4/10/2025 7:37:36 AM -07:00 | 4/29/2025 5:40:59 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1509 | Cannot open Narrative document | Closed | Bug | 4/10/2025 7:41:19 AM -07:00 | 4/29/2025 5:40:59 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2159 | Polaris: Case Management: Cases created via Quick Create do not generate case number. | Closed | Bug | 5/22/2025 10:42:49 PM -07:00 | 6/16/2025 3:16:52 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2482 | Polaris: Case Management: Case report missing currency format for Property Loss Amount field | Dev Complete | Bug | 6/16/2025 7:38:41 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2216 | Case Management: Unable to generate case report for individuals. | Closed | Bug | 6/2/2025 7:33:33 AM -07:00 | 6/17/2025 11:46:58 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2218 | Case Management: Case Report UI issues | Closed | Bug | 6/2/2025 7:52:19 AM -07:00 | 6/17/2025 11:49:41 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2219 | Case Management: Remove Supplemental section and Agent Report Numbers sections from the Supplemental Case Report | Closed | Bug | 6/2/2025 7:59:52 AM -07:00 | 6/17/2025 11:50:59 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 1839 | Case Management: Create Case-Able to choose a date in the future for all Date fields | Closed | Bug | 5/6/2025 11:56:41 AM -07:00 | 6/15/2025 2:43:59 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2507 | 2496 | Polaris: Case Management: Ensure the case reports header matches the sample report provided by the business team. | New | Bug | 6/17/2025 2:43:19 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2199 | Polaris: Case Management: Ensure the case reports have the format specified by the business team. | Closed | Bug | 5/29/2025 2:00:39 PM -07:00 | 6/17/2025 3:15:03 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2474 | Polaris: Case Management: Supplemental case is missing the number suffix | Closed | Bug | 6/13/2025 1:16:40 PM -07:00 | 6/19/2025 6:25:15 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2485 | Polaris: Case Management: Related cases for an individual is shown in duplicates. | Dev Complete | Bug | 6/17/2025 7:30:40 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1581 | Violation Type = Tribal State Compact missing | Closed | Bug | 4/14/2025 12:55:32 AM -07:00 | 4/29/2025 5:40:59 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1582 | Change in Violation Type should update Description field | Closed | Bug | 4/14/2025 12:59:44 AM -07:00 | 4/29/2025 5:40:59 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2176 | Polaris: Case Management: Document Category items are missing for Attachments. | Closed | Bug | 5/27/2025 1:09:28 PM -07:00 | 5/30/2025 3:00:00 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1510 | Display of Criminal status screen | Testing - QA | Bug | 4/10/2025 7:58:31 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2158 | Polaris: Case Management: Locked fields allow edits. | Closed | Bug | 5/22/2025 9:55:55 PM -07:00 | 5/30/2025 3:10:01 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2217 | Case Management: Duplicate Supplemental Reports are generated. | New | Bug | 6/2/2025 7:40:16 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2157 | Polaris: Case Management: Year field has incorrect format in Vehicle form | Closed | Bug | 5/22/2025 9:09:36 PM -07:00 | 6/10/2025 1:13:05 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2173 | Polaris: Case Management -Clicking on +New Narrative Legacy section under Narrative tab has caused an error | Closed | Bug | 5/27/2025 12:16:07 PM -07:00 | 6/10/2025 3:14:57 PM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1917 | Round Robin Index required fields | Closed | Bug | 5/9/2025 6:47:38 AM -07:00 | 5/20/2025 1:55:16 PM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1932 | Round Robin: Populate the 'Assigned Licensing Specialist' for the child organization upon round robin submission when parent organization has it available. | Closed | Bug | 5/9/2025 1:32:07 PM -07:00 | 5/12/2025 6:26:54 AM -07:00 | 5/12/2025 6:26:54 AM -07:00
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2502 | 1177 | Individual license templates back page should not have header and footer | Closed | Bug | 2/27/2025 5:10:16 AM -08:00 | 3/4/2025 7:16:54 AM -08:00 | 3/3/2025 7:07:34 AM -08:00
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2502 | 1178 | Individual License - Sub contractor template is displaying grids | Closed | Bug | 2/27/2025 6:31:42 AM -08:00 | 3/4/2025 7:16:32 AM -08:00 | 3/3/2025 11:05:01 AM -08:00
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2502 | 1179 | All Individual License templates should format the address under 'Licensed at' or 'Display at' | Closed | Bug | 2/27/2025 6:43:22 AM -08:00 | 3/4/2025 7:11:26 AM -08:00 | 3/3/2025 11:04:53 AM -08:00
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2502 | 1180 | Individual Class III Conditional license template is missing 'Display at' address and a colon mark | Closed | Bug | 2/27/2025 6:44:41 AM -08:00 | 3/4/2025 7:09:59 AM -08:00 | 3/3/2025 11:04:45 AM -08:00
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2123 | Employee Application - New or returned by employer should display 'Type of Discharge' option set | Closed | Bug | 5/20/2025 7:09:39 AM -07:00 | 5/22/2025 8:47:36 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2117 | Selected option for 'Alias name' field selected by the employee should displayed for the employer (super or secondary user) | Closed | Bug | 5/19/2025 2:05:45 PM -07:00 | 5/22/2025 8:58:06 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2116 | Enable individual application tabs for Super or secondary user to view the employee submitted details | Closed | Bug | 5/19/2025 1:45:30 PM -07:00 | 5/22/2025 9:03:19 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2126 | Auto-populate the date field provided in the 'Employer Authorization' tab for the Super or Secondary user when they enter their signatures | Removed | Bug | 5/20/2025 12:43:57 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2125 | When employee receives the rejected application for 'corrections needed, the date and signature field should be cleared | Closed | Bug | 5/20/2025 8:43:40 AM -07:00 | 5/22/2025 8:43:26 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2148 | The employee application should retain its contact details when super or secondary user receive the application | Closed | Bug | 5/22/2025 10:22:03 AM -07:00 | 5/29/2025 8:24:28 AM -07:00 | 5/29/2025 8:09:23 AM -07:00
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2124 | Individual Application - When employee open a returned application for edits, they should be navigated to the 'License Type' tab by default | Closed | Bug | 5/20/2025 7:49:25 AM -07:00 | 5/29/2025 8:42:01 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2146 | Answers made by the employee are not available for the employer to view when employee submits the application | Closed | Bug | 5/22/2025 8:30:39 AM -07:00 | 5/29/2025 10:30:30 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2174 | CRM: Individual application business process flow is missing 'Approver' field | Closed | Bug | 5/27/2025 12:53:01 PM -07:00 | 5/29/2025 10:16:07 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2155 | Portal: Secondary user does not have an option to 'Approve' or 'Reject' when the status is 'Pending Employer Approval' | Closed | Bug | 5/22/2025 12:25:55 PM -07:00 | 5/29/2025 8:29:38 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2177 | CRM: The 'Requested By' field for Suitability 1 should populate the service account detail and not any specific user | Closed | Bug | 5/27/2025 1:53:20 PM -07:00 | 5/29/2025 10:37:16 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP | 1365 | SharePoint: Documents should be available under 'Document' header with its name in hyperlink format. | Non Issue | Bug | 3/24/2025 11:57:06 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2195 | Documents uploaded by employee are not opening for Licensing Specialist in CRM or employer (Super pr Secondary user) | Closed | Bug | 5/29/2025 6:22:31 AM -07:00 | 6/2/2025 7:16:45 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2147 | Documents uploaded by the employee are not available for the employer to view when employee submits the application | Closed | Bug | 5/22/2025 8:33:47 AM -07:00 | 6/2/2025 7:15:26 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2185 | Round Robin or LS Assignment should populate the Assigned Licensing Specialist and update the internal & external status field on the application | Closed | Bug | 5/28/2025 2:54:23 PM -07:00 | 6/2/2025 8:10:08 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2196 | CRM: Individual Application 'Checklist' tab is missing notes section | Closed | Bug | 5/29/2025 6:29:24 AM -07:00 | 6/2/2025 6:33:49 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP | 2327 | CRM: Individual Application field locks | Removed | Bug | 6/6/2025 6:00:00 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP | 2312 | CRM: Individual application should save the Alias Name information added in the CRM Summary tab under Individual details | Removed | Bug | 6/5/2025 3:07:05 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP | 2303 | CRM: Summary tab of individual application submitted is not matching the license type questions | Removed | Bug | 6/5/2025 2:47:44 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 1243 | The document name for the generated license should include the License Number | Closed | Bug | 3/4/2025 8:39:42 AM -08:00 | 6/11/2025 10:47:00 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2328 | CRM: Checklist issues | Dev Complete | Bug | 6/6/2025 6:26:49 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2504 | CRM: Missing question for Ancillary Sports Wagering Representative | Dev Ready | Bug | 6/18/2025 7:33:20 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2505 | CRM: Employer Authorization spelling correction | Dev Complete | Bug | 6/18/2025 7:42:44 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2510 | CRM: Individual License Questions are not fully displayed | Dev Complete | Bug | 6/18/2025 2:08:50 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2508 | CRM: Individual Contact form should be updated with Military information and Alias | Removed | Bug | 6/18/2025 8:54:58 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2509 | CRM: Lock the Criminal History Detail fields & Alias Name Detail fields | Dev Ready | Bug | 6/18/2025 1:49:35 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2269 | Case Management: Unable to create a case with " Subject unknown" checkbox checked. | Closed | Bug | 6/4/2025 2:12:29 PM -07:00 | 6/6/2025 6:12:49 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2111 | Polaris: Case Management -Fields lock permissions to be revised for a Case. | Dev Complete | Bug | 5/16/2025 2:23:32 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1511 | Attachments for Cases do not have Document Types | Closed | Bug | 4/10/2025 8:03:40 AM -07:00 | 4/29/2025 5:40:59 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1538 | NIBRS Lookup values | Closed | Bug | 4/11/2025 8:36:17 AM -07:00 | 4/29/2025 5:40:59 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1234 | Case Information Tab - Incident Details dropdown | Closed | Bug | 3/4/2025 6:20:08 AM -08:00 | 3/17/2025 12:34:27 PM -07:00 | 3/17/2025 12:34:27 PM -07:00
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1235 | Case Information Tab - Date Occurred field | Closed | Bug | 3/4/2025 6:26:05 AM -08:00 | 3/10/2025 8:50:36 AM -07:00 | 3/10/2025 8:50:36 AM -07:00
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2511 | Polaris: Case Management: Tip Line: Date of Violation accepts future and time. | New | Bug | 6/18/2025 10:06:54 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2198 | Add Documents to Reply does not open the upload document dialog box | Testing Complete - QA | Bug | 5/29/2025 10:38:14 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1660 | Data Configuration: Date of Seizure should become a required field when Case Type is Civil | Closed | Bug | 4/29/2025 9:34:19 AM -07:00 | 5/1/2025 5:35:33 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1539 | Dispositions for Case Type = Criminal not displaying correctly | Closed | Bug | 4/11/2025 8:40:32 AM -07:00 | 5/13/2025 10:21:25 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1537 | Dispositions for Case Type = Civil not displaying correctly | Closed | Bug | 4/11/2025 8:25:23 AM -07:00 | 5/22/2025 11:39:13 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1681 | Case Management: Address fields in Location of Incident tab should match the fields from Field listing. | Non Issue | Bug | 5/1/2025 9:06:41 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1683 | Case Management: Missing Address fields For Unknown subject when Case Category is "Unlicensed" | Closed | Bug | 5/1/2025 9:27:58 AM -07:00 | 5/23/2025 7:12:28 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1236 | Vehicle Tab | Closed | Bug | 3/4/2025 6:45:08 AM -08:00 | 3/20/2025 7:16:58 AM -07:00 | 3/20/2025 7:16:58 AM -07:00
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1286 | Case Information Tab: Missing "Primary Activity" field | Closed | Bug | 3/10/2025 8:56:31 AM -07:00 | 3/19/2025 7:09:27 AM -07:00 | 3/17/2025 9:22:09 AM -07:00
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1317 | Dispositions - Duplicate Values | Closed | Bug | 3/13/2025 8:05:10 AM -07:00 | 3/17/2025 12:39:13 PM -07:00 | 3/17/2025 9:23:23 AM -07:00
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1506 | Cannot see High priority checklist uploaded to the case | Closed | Bug | 4/10/2025 7:18:10 AM -07:00 | 4/29/2025 5:40:12 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1687 | Case Management: Missing Capitalization for Incident Details item. | Closed | Bug | 5/1/2025 11:32:02 AM -07:00 | 5/29/2025 10:05:24 AM -07:00 | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2184 | Secure Message Grid Name in Submission Record | Closed | Bug | 5/28/2025 1:41:43 PM -07:00 | 5/29/2025 11:36:55 AM -07:00 | null
GMB Project by MERP\Team Ace of Spades | Senthurpandi, Janar (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1728 | The QLR Number should automatically be generated | Resolved | Bug | 5/5/2025 3:55:01 PM -07:00 | null | 5/12/2025 6:48:32 AM -07:00
GMB Project by MERP\Team Black Jack | Senthurpandi, Janar (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1475 | Testing Standard: Required Fields must be filled in error | Closed | Bug | 4/8/2025 10:40:46 AM -07:00 | 4/22/2025 10:33:18 AM -07:00 | 4/21/2025 6:58:10 AM -07:00
GMB Project by MERP\Team Black Jack | Smith, Charles (GMB) | GMB Project by MERP\Sprint 2505 | 1848 | Case Management: New Item inputs are blocked by 'Save and Continue' | Non Issue | Bug | 5/6/2025 4:16:48 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Taylor, Todd (GMB) | GMB Project by MERP\Sprint 2505 | 2078 | Case Management: Test Case 1579 (MERP) 1851 (GMB) Case Management - Create Case Narrative - Script errors | Cannot Recreate | Bug | 5/15/2025 11:27:34 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Taylor, Todd (GMB) | GMB Project by MERP\Sprint 2502 | 2086 | Test Case 1441 (MERP) 1949 (GMB) My Account: Switch Profiles - Cannot Switch Access on Invalid Pages | Cannot Recreate | Bug | 5/15/2025 2:22:21 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Taylor, Todd (GMB) | GMB Project by MERP\Sprint 2502 | 2034 | Test case 1560 (MERP) 2004 (GMB) MyAccount: USPS Address Validation for Organization and Individual - Incorrect Prompt/Message on Invalid Address | Duplicate | Bug | 5/14/2025 12:01:54 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Taylor, Todd (GMB) | GMB Project by MERP\Sprint 2502 | 2049 | Test Case 1463 (MERP) 1753 (GMB) My Account: Non-Tribal: Super User Dashboard and Menu options - Missing button, column in system not in test | Non Issue | Bug | 5/14/2025 3:53:39 PM -07:00 | null | null
GMB Project by MERP\Team GMB | Taylor, Todd (GMB) | GMB Project by MERP\Sprint 2502 | 1531 | Not able to enter data in Primary Activity field | Closed | Bug | 4/11/2025 5:59:01 AM -07:00 | 4/14/2025 8:47:56 AM -07:00 | null
GMB Project by MERP\Team Maverick | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1360 | Update the labels to match the labels with user story requirement | Closed | Bug | 3/23/2025 8:32:21 PM -07:00 | 3/24/2025 8:13:44 PM -07:00 | 3/24/2025 8:13:37 PM -07:00
GMB Project by MERP\Team GMB | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2229 | SSO not working | Resolved | Bug | 6/2/2025 1:16:35 PM -07:00 | null | 6/3/2025 5:13:54 PM -07:00
GMB Project by MERP\Team Black Jack | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP | 1837 | Create Case- Case Type Dropdown not populating | Non Issue | Bug | 5/6/2025 11:45:04 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP | 1840 | Create Case- Incident Details Dropdown not populating | Non Issue | Bug | 5/6/2025 11:58:27 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP | 1838 | Test Case 1577 (MERP) 1724 (GMB) Account Management: Create Account Alerts - Incident Type Dropdown not populating | Non Issue | Bug | 5/6/2025 11:47:47 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP\Sprint 2507 | 2483 | Polaris: Case Management: Narrative section of the Case Report is missing page footer . | New | Bug | 6/16/2025 8:44:05 PM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP | 2082 | Create Case- No Save or Submit button in the expected location | Non Issue | Bug | 5/15/2025 1:10:44 PM -07:00 | null | null
GMB Project by MERP | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1435 | Error while saving new organization | Closed | Bug | 4/2/2025 9:48:14 AM -07:00 | 4/11/2025 1:53:31 PM -07:00 | 4/6/2025 8:05:53 PM -07:00
GMB Project by MERP\Team Maverick | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1454 | Missing Audit History for Suitability 2 | Closed | Bug | 4/6/2025 8:52:28 PM -07:00 | 4/7/2025 6:42:48 AM -07:00 | null
GMB Project by MERP\Team Maverick | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1455 | Missing Audit History for Suitability 1 | Closed | Bug | 4/6/2025 8:55:02 PM -07:00 | 4/7/2025 6:41:14 AM -07:00 | 4/7/2025 6:41:08 AM -07:00
GMB Project by MERP\Team Maverick | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1333 | Suitability 1 - Replace the word "Result" with "Review" for task UI | Closed | Bug | 3/16/2025 3:46:08 PM -07:00 | 3/20/2025 10:02:10 AM -07:00 | 3/17/2025 2:39:17 PM -07:00
GMB Project by MERP\Team Maverick | William, Richard (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2261 | My Account Submission Withdrawal | New | Bug | 6/4/2025 7:10:18 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | William, Richard (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1230 | Individual license templates are missing colon sign after License Type and require space after 'Certified at' or 'Display at' | Closed | Bug | 3/3/2025 12:57:37 PM -08:00 | 3/12/2025 12:22:15 PM -07:00 | 3/12/2025 12:22:15 PM -07:00
GMB Project by MERP\Team Maverick | William, Richard (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1231 | Individual Eligibility Letter - Fine tune spacing and add the eligibility number | Closed | Bug | 3/3/2025 2:11:23 PM -08:00 | 3/12/2025 2:04:54 PM -07:00 | 3/12/2025 2:04:54 PM -07:00
GMB Project by MERP\Team Maverick | William, Richard (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1232 | Remove 'Director' from the signature samples in select Individual License templates and it should not overlap the footer | Closed | Bug | 3/3/2025 2:15:07 PM -08:00 | 3/12/2025 12:25:08 PM -07:00 | 3/12/2025 12:25:08 PM -07:00
GMB Project by MERP\Team Maverick | William, Richard (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1341 | Suitability 2 - Internal and External statuses are not populated when a new task is created and saved. | Closed | Bug | 3/17/2025 1:03:35 PM -07:00 | 3/20/2025 1:01:50 PM -07:00 | 3/20/2025 1:01:50 PM -07:00
GMB Project by MERP\Team Maverick | Bouzos, Sofia (GMB Contractor) | GMB Project by MERP | 2071 | Test case 1262 (MERP) 1978 (GMB) Submissions: New/Upgrade Software and Equipment Submissions Non-TLS - Legal Rights Upload Not Required | Non Issue | Bug | 5/15/2025 10:12:53 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Chute, Naren (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1330 | Individual License generated should be available on Individual Contact form in CRM | Closed | Bug | 3/14/2025 2:16:25 PM -07:00 | 3/24/2025 11:46:13 AM -07:00 | 3/24/2025 11:46:13 AM -07:00
GMB Project by MERP\Team Ace of Spades | Dash, Ankita (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2093 | Test case 1641 (MERP) 1929 (GMB) Test Case: Setup Fees - Duplicate Name Selection | Resolved | Bug | 5/15/2025 3:51:49 PM -07:00 | null | 5/21/2025 5:31:14 AM -07:00
GMB Project by MERP\Team Maverick | Dugand, Roberto (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1258 | Application Oath Page- Signature date not captured after user signs the application. | Closed | Bug | 3/5/2025 2:49:43 PM -08:00 | 4/18/2025 1:51:51 PM -07:00 | null
GMB Project by MERP\Team GMB | Hansen, Spencer (GMB) | GMB Project by MERP\Sprint 2506 | 2417 | Polaris GMB UAT - Polaris Account Management: New Organization- inability to add an address for premise | New | Bug | 6/11/2025 11:11:08 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Johnson, Zakia (GMB Contractor) | GMB Project by MERP | 2064 | MyAccount: User is able to select a future dated authorized signatory date. | Deferred | Bug | 5/15/2025 8:23:05 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | Konduru, Sujitha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1306 | Clicking 'Validate' on Contact Information Page with invalid address Triggers Pop-up with Error: Something went wrong. Please try again. | Closed | Bug | 3/11/2025 2:33:52 PM -07:00 | 5/5/2025 6:13:23 AM -07:00 | null
GMB Project by MERP\Team Maverick | Koppuravuri, Sai (GMB Contractor) | GMB Project by MERP\Sprint 2504 | 1253 | My Account 'License status' not updated to 'Expire' when the expiration date was in past. | Closed | Bug | 3/5/2025 10:54:44 AM -08:00 | 3/31/2025 5:52:02 AM -07:00 | 3/31/2025 5:52:02 AM -07:00
GMB Project by MERP\Team Black Jack | Lin, Yaoshi (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1679 | Non-Tribal Secondary User: QLR Filer: Dashboard: QLR Reminders grid not present | Closed | Bug | 5/1/2025 8:18:34 AM -07:00 | 5/28/2025 12:54:54 PM -07:00 | null
GMB Project by MERP\Team Black Jack | Nirmal, Kesha (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1834 | MyAccount: Applications_ When switching the roles the user is landed on the Previous user page | Closed | Bug | 5/6/2025 10:35:42 AM -07:00 | 5/29/2025 10:03:36 AM -07:00 | null
GMB Project by MERP | Padmanabhan, Soumya (GMB Contractor) | GMB Project by MERP | 1434 | GMB UAT Test Data | Non Issue | Bug | 4/2/2025 9:41:10 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Piao, Li (GMB Contractor) | GMB Project by MERP\Sprint 2506 | 2225 | Case Management: Staff and Supervisor for supplement case should be the supplemental case agent and their supervisor. | Closed | Bug | 6/2/2025 12:10:54 PM -07:00 | 6/11/2025 6:31:43 AM -07:00 | null
GMB Project by MERP\Team Maverick | Saxena, Shikha (GMB Contractor) | GMB Project by MERP\Sprint 2508 | 2506 | CRM: Alias Name response is 'Yes' but CRM is still showing 'No' | Deferred | Bug | 6/18/2025 7:49:55 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | Schondorf, Larry (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 2108 | Case Management: Incident Area field is not locked and allows users to change or add new values after a save. | Closed | Bug | 5/16/2025 9:04:36 AM -07:00 | 6/2/2025 9:39:34 AM -07:00 | null
GMB Project by MERP\Team Ace of Spades | Senthurpandi, Janar (GMB Contractor) | GMB Project by MERP\Sprint 2505 | 1732 | Fee Table ID under GMB fee table should be automatically created | Resolved | Bug | 5/5/2025 4:04:25 PM -07:00 | null | 5/12/2025 6:49:27 AM -07:00
GMB Project by MERP\Team GMB | Smith, Charles (GMB) | GMB Project by MERP\Sprint 2504 | 1831 | TC1577- No steps fail | Removed | Bug | 5/6/2025 9:46:42 AM -07:00 | null | null
GMB Project by MERP\Team GMB | Taylor, Todd (GMB) | GMB Project by MERP\Sprint 2503 | 1557 | No investigations tab to select | Non Issue | Bug | 4/11/2025 3:55:55 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | Vuyyuru, Santhi (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1334 | Suitability 1 - Delete the options that are invalid for "Review" drop-down | Closed | Bug | 3/16/2025 6:41:14 PM -07:00 | 3/20/2025 11:00:38 AM -07:00 | 3/17/2025 2:39:28 PM -07:00
GMB Project by MERP\Team Maverick | William, Richard (GMB Contractor) | GMB Project by MERP\Sprint 2503 | 1355 | Update columns for profile view for Suitability 1 & 2 to match the requirements | Closed | Bug | 3/20/2025 11:27:33 AM -07:00 | 3/20/2025 12:58:18 PM -07:00 | 3/20/2025 12:58:18 PM -07:00
GMB Project by MERP\Team Maverick | null | GMB Project by MERP\Sprint 2508 | 1242 | Individual Licenses should be displayed in descending order, displaying the latest added document at the top | Deferred | Bug | 3/4/2025 8:28:11 AM -08:00 | null | null
GMB Project by MERP\Team Maverick | null | GMB Project by MERP\Sprint 2508 | 1682 | Organization License Template: Display at address should include Street 2 and 3 line if applicable | Deferred | Bug | 5/1/2025 9:18:53 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | null | GMB Project by MERP\Sprint 2508 | 1709 | Documentation tab: Uploaded Documents listed in Incorrect Order | Deferred | Bug | 5/2/2025 2:21:30 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | null | GMB Project by MERP\Sprint 2507 | 1680 | Organization templates - Missing lowercase, commas and colons & font type sizing | Deferred | Bug | 5/1/2025 8:38:43 AM -07:00 | null | null
GMB Project by MERP\Team Maverick | null | GMB Project by MERP\Sprint 2507 | 1446 | USPS Address Validation: Incorrect Header In pop-up and Label for Street address field should "Street Address" instead of "StreetAddress" | Deferred | Bug | 4/3/2025 7:21:52 PM -07:00 | null | null
GMB Project by MERP | null | GMB Project by MERP | 1433 | Error while saving new organization | Removed | Bug | 4/2/2025 9:35:40 AM -07:00 | null | null
GMB Project by MERP | null | GMB Project by MERP | 1432 | Test Data | Removed | Bug | 4/2/2025 9:33:35 AM -07:00 | null | null
GMB Project by MERP\Team Black Jack | null | GMB Project by MERP\Sprint 2506 | 2484 | Polaris: Case Management: Individual "Subject" should be mapped to "Subject/Suspect" of Code and to be displayed under Persons section of the report. | New | Bug | 6/16/2025 9:21:38 PM -07:00 | null | null
GMB Project by MERP\Team Maverick | null | GMB Project by MERP\Sprint 2505 | 1675 | MyAccount: Employee-Contact Information Tab: After adding the Alternate name, Resets 'Has your employee ever used a different name?' Field to Blank | Closed | Bug | 4/30/2025 9:00:34 PM -07:00 | 5/30/2025 6:20:33 AM -07:00 | null
GMB Project by MERP\Team Maverick | null | GMB Project by MERP\Sprint 2508 | 1420 | Pop-Up Fails to Specify or Highlight Incorrect Fields During Address Validation in CRM. | Dev Ready | Bug | 4/1/2025 8:10:18 AM -07:00 | null | null